## Sheet1
Security Objectives Register
CloudNova Technologies
Per ISO/IEC 27001 Clause 6.2
Review Date: 2026-07-18
Objective ID | Objective (SMART) | Owner | Target Date | Measurement Method | Current Status
O-001 | Achieve 100% MFA coverage for all privileged accounts and at least 98% coverage for standard user accounts across AWS, Microsoft 365, and other critical systems. | IT & Security Manager | 2026-12-31 | Percentage of active accounts protected by MFA, measured through IAM and identity-platform reports. | Not Started
O-002 | Reduce the number of critical and high-severity vulnerabilities remaining beyond their approved remediation deadline by at least 90%. | Head of Engineering / Security Manager | 2026-12-31 | Monthly vulnerability-management reports comparing overdue vulnerabilities against the baseline. | Not Started
O-003 | Achieve 100% completion of annual information-security awareness training for all employees and contractors. | HR Manager / Security Manager | 2026-11-30 | Training completion records and learning-management-system reports. | Not Started
O-004 | Ensure that 100% of critical information assets and systems have an identified owner, classification, and documented security requirements. | Information Security Manager | 2026-10-31 | Quarterly review of the information-asset inventory. | Not Started
O-005 | Complete security risk assessments for 100% of critical third-party vendors and ensure that identified high risks have documented treatment plans. | Procurement / GRC Manager | 2026-12-31 | Vendor-risk register and completed supplier assessments. | Not Started
O-006 | Conduct at least one full incident-response exercise and one business-continuity/disaster-recovery exercise for critical SaaS operations. | Security Manager / IT Operations Manager | 2026-11-30 | Exercise completion records, results, identified gaps, and corrective-action tracking. | Not Started
O-007 | Achieve 100% completion of quarterly access reviews for privileged access to AWS, Microsoft 365, production systems, and other critical applications. | IT Operations Manager | 2026-12-31 | Quarterly access-review records and remediation evidence. | Not Started
O-008 | Maintain 100% completion of required PCI DSS control testing and evidence collection for applicable in-scope systems and processes. | Compliance / GRC Manager | 2026-12-31 | PCI DSS compliance tracker, control-testing results, and evidence records. | Not Started
O-009 | Ensure that 100% of critical production systems have tested backup and recovery procedures with documented recovery results. | IT Operations / Cloud Infrastructure Manager | 2026-10-31 | Backup monitoring reports and documented recovery-test results. | Not Started
O-010 | Ensure that 100% of identified ISMS nonconformities and corrective actions are assigned an owner and tracked to closure within their approved target date. | GRC Manager | 2026-12-31 | Corrective-action register and monthly status reviews. | Not Started
Document Owner: GRC Function
Approved By: CEO