## Sheet1
Deficiency Log
Deficiency ID | Control ID | Description | Severity | Root Cause | Owner | Remediation Plan | Target Date | Status | Re-Test Date
D-001 | C-010 | Several non-critical servers exceeded the organization's 30-day patching standard. | Medium | Manual patch scheduling and insufficient monitoring. | IT Operations Manager | Implement automated patch compliance monitoring and monthly management review. | 2026-08-15 | Open | 2026-08-20
D-002 | C-014 | Annual security reassessments for two existing vendors were not completed on schedule. | Medium | Lack of a formal vendor reassessment calendar and automated reminders. | Vendor Risk Manager | Establish a vendor review schedule with automated notifications and management oversight. | 2026-08-01 | Open | 2026-08-08
D-003 | C-017 | Annual incident response tabletop exercise was not conducted within the required timeframe. | Medium | Testing schedule was not tracked or assigned to an owner. | Information Security Manager | Conduct a tabletop exercise, document lessons learned, and implement corrective actions. | 2026-08-31 | Open | 2026-09-07
D-004 | C-008 | SIEM alert rules generate excessive false positives, reducing monitoring efficiency. | Low | Default alert rules have not been reviewed or tuned. | Security Operations Manager | Review and optimize SIEM correlation rules and alert thresholds. | 2026-08-20 | Open | 2026-08-27
D-005 | C-020 | Quarterly access review records are not consistently documented or approved. | Low | No standardized documentation process or approval workflow. | IT Manager | Implement standardized access review templates and management sign-off. | 2026-08-10 | Open | 2026-08-17

## Sheet2
Remediation Tracker
Deficiency ID | Related Control ID | Deficiency | Remediation Action | Owner | Start Date | Target Date | % Complete | Status | Verified By
D-001 | C-010 | Non-critical servers not patched within the required 30-day timeframe | Implement automated patch compliance monitoring and monthly management review | IT Operations Manager | 2026-07-20 | 2026-08-15 | 25% | In Progress | Information Security Manager
D-002 | C-014 | Annual security reassessments for existing vendors are overdue | Establish a vendor reassessment schedule with automated reminders | Vendor Risk Manager | 2026-07-18 | 2026-08-01 | 10% | In Progress | Head of Risk & Compliance
D-003 | C-017 | Annual incident response tabletop exercise not conducted | Conduct tabletop exercise, document lessons learned, and update the Incident Response Plan | Information Security Manager | 2026-07-22 | 2026-08-31 | 0% | Not Started | Chief Information Security Officer
D-004 | C-008 | SIEM alert tuning requires improvement to reduce false positives | Review and optimize SIEM correlation rules and alert thresholds | Security Operations Manager | 2026-07-25 | 2026-08-20 | 15% | In Progress | Information Security Manager
D-005 | C-020 | Quarterly access review documentation is inconsistent | Standardize access review documentation and implement management sign-off | IT Manager | 2026-07-21 | 2026-08-10 | 40% | In Progress | Internal Auditor